## Ghant Chart
2022
|  | January |  |  |  |  | February |  |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
Set-up
Script setup | Pedro | bar: January 1 to April 18
Training | Pedro | bar: January 1 to May 23
1. Stress according to species
Beta diversity | Zulema | bar: January 3 to March 14
Alpha diversity | Zulema | bar: January 3 to March 14
Neutral models | Marcela | bar: February 9 to April 15
Deseq2 | Melissa | bar: February 9 to March 13
Network structure changes | Pedro | bar: April 15 to May 19
1.a Additional tests
Soil sample analysis | Pedro
Phylogeny
Phylogeny reconstruction | Marcela | bar: January 2 to February 6
Phylogenetic signal | bar: January 5 to February 6
Shared microbiome response
Core microbiome definition | Zulema
Pilot project
Holidays | bar: January 1 to January 2; July 28 to July 29; December 51 to December 53
Total

## Overview
1st part of analysis | [6 empty] | Additional analysis |  |  |  | Milestone period 3 May-August 2022
Activities | Analysis | Resources | Priority | Approach | Time | Risks | Activities | Analysis | Resources | Risks | Activities | Analysis | Resources | Risks | Activities | Resources | Risks
Stress according to species | Beta diversity(if they differ) | Zulema, Pedro | 1 |  |  | Genome Quebec delivery, our own projects, time, knowledge gap (big), computer power. | Phylogeny |  |  |  | Shared microbiome stress responses | Ternary plots
| Neutral models (which are selected) | Marcela, Pedro | 1 | Subset (3-4) to run the code. Selection under Control, MeJA and SA (above expected). Plot simmilarity of selected communities. Repeat in 34 species.
| Deseq2 (which are more abundant) | Melissa, Pedro | 1 | Deseq from Zimb-Wave. 1. Subset to run the code, 2. comparison of: Control vs MeJA and Control vs SA. 3. Plots for 34 species
| Network structure changes (role of keystone species) | Pedro | 1
Soil samples analysis |  | Pedto
| Alpha diversity | Zulema, Pedro | 2 | Same as for Beta diversity
| Random forest | Melissa, Pedro, Chratz | 2
| Matrix of heat trees |  | 2
Phylogeny | Reconstructing phylogeny | Marcela, Karen, Klaas | 1
Phylogenetic distances
Phylogenetic signal